## Sinteza
# | Categorie | Componenta software | PagCS | Cerinta CdS (rezumat) | Produs recomandat (oferta) | Alternativa | Cantitate / Sizing | Unitate licentiere | Locatie implementare | Sursa CdS (sectiune) | Intrebari / Observatii
1 | A. Infrastructura SW | Sistem de operare server (Linux) | pg.52-53 | OS 64-bit, IPv6, cluster, COTS. | RHEL 9 / Oracle Linux 9 | Ubuntu LTS / SUSE | 20-30 VM-uri | Per socket | Cloud guv. (BYOL) | 3.4.3.2.3 | Matricea apl->OS nu e specificata
2 | A. Infrastructura SW | Sistem de operare server (Windows) | pg.52-53; pg.101-105 | 4 instante honeypot + MS components. | Win Server 2022 DC | Win Server 2022 Std | Min. 4 + 6-10 VM | Per core + CAL | Cloud + Centrul | 3.4.3.2.3 | Propunem majoritate Linux
3 | A. Infrastructura SW | Platforma web server | pg.51-52 | Cluster activ-activ, 16 nuclee/nod. | NGINX Plus | Apache / IIS | 2 × 16 cores | Per instanta | Cloud guv. | 3.4.3.2.1 | Cluster 2 sau 3?
4 | A. Infrastructura SW | Server aplicatie | pg.52 | Cluster activ-activ. | Oracle WebLogic | JBoss EAP / WAS | 2 × 16 cores | Per processor | Cloud guv. | 3.4.3.2.2 | WebLogic vs JBoss?
5 | A. Infrastructura SW | SGBD principal | pg.53-55 | Gartner Leaders, cache fusion, TDE. | Oracle DB EE + RAC | MSSQL EE + Always On (risc) | 2 × 8 cores | Per processor | Cloud guv. | 3.4.3.2.4 | Cache fusion = RAC
6 | A. Infrastructura SW | SGBD NoSQL | pg.110 | Log-uri NoSQL. | Elasticsearch | MongoDB / OpenSearch | Cluster 3 noduri | Per nod | Cloud guv. | 3.4.3.4.1.4 | Volum log?
7 | A. Infrastructura SW | ETL | pg.55-57 | Multi-DB; ELT in destinatie. | Oracle Data Integrator | Informatica / Talend | 16 cores | Per processor | Cloud guv. | 3.4.3.2.5 | Cuplat cu SGBD
8 | A. Infrastructura SW | BI | pg.57-59 | 50 useri. | Oracle Analytics | Power BI / Tableau / Qlik | 50 useri | Per named user | Cloud guv. | 3.4.3.2.6 | Named vs concurrent?
9 | A. Infrastructura SW | IAM | pg.59-60 | LDAP, OIDC, OAuth2, SAML. | Keycloak Enterprise | Entra ID / Oracle IAM | 150 + 185k | Per user | Cloud guv. | 3.4.3.2.7 | 185k cetateni separat?
10 | A. Infrastructura SW | Sistem GIS | pg.60-62 | Cartografiere; layere. | ESRI ArcGIS | GeoServer + PostGIS | 1 server + 50 editori | Per server | Cloud guv. | 3.4.3.2.8 | Cati editori?
11 | A. Infrastructura SW | ESB | pg.62-65 | Cluster activ-pasiv. | Oracle Service Bus | MuleSoft / WSO2 | 2 × 16 cores | Per processor | Cloud guv. | 3.4.3.2.9 | Activ-pasiv?
12 | B. Software aplicativ | DMS | pg.65-83 | 7 module; multi-DB; web+PWA. | VOGO ENTERPRISE BUSINESS SUITE | (produs propriu) | Nelimitat + cod sursa | Perpetuu | Cloud guv. | 3.4.3.3.1 | VOGO indeplineste
13 | B. Software aplicativ | Portal | pg.83-86 | Cetateni/firme/medici vet; SSO; ROeID. | Modul VOGO Portal | Liferay / Drupal | Nelimitat | Perpetuu | Cloud guv. | 3.4.3.3.2 | Vezi sheet Portal
14 | B. Software aplicativ | Chatbot | pg.86-87 | NLP RO; auto-raspuns. | Rasa / MS Bot Framework | Dialogflow / Watson | 1 instanta | Per instanta | Cloud guv. | 3.4.3.3.2.1 | Min 50 intents kickoff?
15 | B. Software aplicativ | Aplicatie mobila | pg.87-88 | Nativ iOS + Android + PWA. | Nativ Swift + Kotlin + PWA | Flutter / RN | Free + 99$/an | Per Dev Account | Stores | 3.4.3.3.2.2 | Vezi sheet App
16 | B. Software aplicativ | LIMS | pg.88-94 | Lab veterinar; HL7. | Custom VOGO | Modulo / STARLIMS | Nelimitat + cod sursa | Perpetuu | Cloud + lab | 3.4.3.3.3 | In-house dezvoltat
17 | B. Software aplicativ | HL7 gateway | pg.94-96 | Gateway BD <-> HL7. | Mirth Connect | InterSystems / Iguana | 1 instanta | Per instanta | Cloud guv. | 3.4.3.3.3.2 | Vezi sheet HL7
18 | C. Securitate (appliance SW) | WAF | pg.98-101 | OWASP Top 10. | F5 / Imperva / FortiWeb | Cloudflare / Akamai | 2 buc | Per appliance | Centrul | 3.4.3.4.1.1 | HA cluster
19 | C. Securitate (appliance SW) | Honeypot | pg.101-105 | 4 Win × 4 vCPU. | FortiDeceptor | SentinelOne / TrapX | 1 + 4 Win | Per appliance | Centrul | 3.4.3.4.1.2 | Win incluse?
20 | C. Securitate (appliance SW) | NMS / NAC | pg.105-108 | Min 600 dev. | Cisco DNA / ClearPass | FortiNAC / Extreme | 1 + 600 | Per device | Centrul | 3.4.3.4.1.3 | ~620 marginal
21 | C. Securitate (appliance SW) | SIEM | pg.108-113 | NoSQL log; IOC 3 ani. | Splunk ES / QRadar | Wazuh / Sentinel | 1 cluster | Per GB/zi | Centrul | 3.4.3.4.1.4 | Volum log determinant
22 | C. Securitate (appliance SW) | Email Security | pg.113-118 | Filtrare; sandbox. | Cisco IronPort | Proofpoint / FortiMail | 2 buc | Per mailbox | Centrul | 3.4.3.4.1.5 | ~1000-1500 mailbox
23 | C. Securitate (appliance SW) | NGFW centru | pg.118-127 | Redundant; 10 VDOM. | FortiGate / Palo Alto | Cisco / Check Point | 2 buc | Per appliance | ANSVSA | 3.4.3.4.2.1.1 | Single-vendor obligator
24 | C. Securitate (appliance SW) | NGFW locatii | pg.127-131 | Redundant 45 locatii. | FortiGate 100F | Palo Alto / CP | 90 buc | Per appliance | DSVSA + Institute | 3.4.3.4.2.1.2 | 45 × 2 = 90
25 | D. Productivity / Client | MS Office laptopuri | pg.144-145 | Office perpetuu. | MS Office H&B 2024 OEM | LibreOffice | 100 buc | Per device | ANSVSA | 3.4.3.4.2.6 | Recomandam Office original
26 | D. Productivity / Client | MS Office complete teren | pg.145-147 | Office perpetuu. | MS Office H&B 2024 OEM | LibreOffice | 336 buc | Per device | DSVSA | 3.4.3.4.2.7 | Total Office = 436
27 | D. Productivity / Client | Antivirus | n/a | Implicit pt. endpoint. | CrowdStrike / SentinelOne | ESET / Bitdefender | 436+50 | Per endpoint | ANSVSA + DSVSA | Implicit | Includem?

## Cantitati explicite CdS
# | Componenta | Cantitate / Limita | Unitate | Sursa CdS | Citat exact
1 | Web server | 16 nuclee/nod | cores | 3.4.3.2.1 | 16 nuclee de procesare per nod
2 | App server | 16 nuclee/nod activ-activ | cores | 3.4.3.2.2 | 16 nuclee per nod
3 | SGBD | 2 noduri × 8 cores | noduri | 3.4.3.2.4 | 2 noduri distincte, minim 8 nuclee
4 | ETL | 16 cores | cores | 3.4.3.2.5 | minim 16 nuclee de procesare
5 | BI | 50 useri | named | 3.4.3.2.6 | 50 de utilizatori
6 | ESB | 16 cores/nod activ-pasiv | cores | 3.4.3.2.9 | cluster activ-pasiv 16 nuclee
7 | LIMS | Nelimitat + perpetuu + 3 ani L2+L3 | useri | 3.4.3.3.3 | numar nelimitat de utilizatori
8 | SW aplicative | Perpetuu + cod sursa | - | 3.4.3.3.4 | licente perpetue + cod sursa integral
9 | WAF | NU per useri | - | 3.4.3.4.1.1 | nu trebuie licentiat per useri
10 | Honeypot | 4 Win × 4 vCPU | instante | 3.4.3.4.1.2 | 4 instante capcana Windows
11 | NMS | Min 600 | devices | 3.4.3.4.1.3 | minimum 600 echipamente
12 | NGFW centru | Min 10 VDOM | VDOM | 3.4.3.4.2.1.1 | 10 instante virtuale
13 | NGFW locatii | Min 10 VDOM/echip | VDOM | 3.4.3.4.2.1.2 | Licenta pentru 10 instante
14 | Laptop | 100 buc | device | 3.4.3.4.2.6 | 100 de laptopuri
15 | Complete teren | 336 (8×42) | device | 3.4.3.4.2.7 | 8 in fiecare DSVSA
16 | Institutii | 46 | - | 3.5 | 46 institutii publice
17 | Useri portal | 185.000/an | useri | 3.5 | 185.000 utilizatori
18 | Servicii electronice | 56 | - | 3.5 | 56 de servicii electronice
19 | Useri instruiti | 144 + 3 admin | useri | 3.5 | 144 utilizatori, 3 administratori
20 | BYOL Azure | Toate COTS BYOL | - | 3.4.3.1 | BYOL prin contract
21 | VALOARE PROIECT | 95.271.200,60 RON | RON | Anexa fin. | Val. totala eligibila
22 | ECHIPAMENTE | Max 20% | RON | Anexa fin. | maxim 20%
23 | SECURITATE | Min 10% | RON | Anexa fin. | minim 10%

## AppMobilaCetateni
Estimare efort - Aplicatie mobila cetateni (3.4.3.3.2.2, pg.87-88 CdS)
Scope: Nativ iOS+Android+PWA; raportare animale salbatice; GPS+GIS central; camera; offline; ROeID+IAM Keycloak; consum ESB async; telemetrie ETL/DW; A11y WCAG 2.1 AA; OWASP MASVS L1; 3 ani garantie.
Faza | Estimat man-day | Risk % | Descriere risc | Note / Livrabile
1. Analiza cerinte + workshop-uri stakeholderi | 22 | 15% | ANSVSA+DSVSA+medici vet; 5-7 workshops | User stories; persona; backlog
2. UX research + wireframes Lo-Fi | 28 | 20% | Material 3 + iOS HIG + WCAG AA; 3-4 iteratii | Wireframes; testing 5-8 useri
3. UI design Hi-Fi + design system | 32 | 15% | Atomic; veterinary icons; 30+ ecrane | Figma; assets; prototype
4. Arhitectura + ADR + setup proiect | 22 | 10% | Nativ obligatoriu; 3 platforme CI/CD | ADR; repo; pipeline; dev accounts
5. Dezvoltare iOS nativ (Swift+SwiftUI) | 75 | 25% | 30+ ecrane; nav, state, persistence | IPA; TestFlight; cov 70%
6. Dezvoltare Android (Kotlin+Compose) | 75 | 25% | 30+ ecrane; Material 3; fragmentare | APK/AAB; Internal Track; cov 70%
7. PWA companion | 35 | 15% | Service workers; offline cache; push web | PWA installabila
8. GPS + harta de baza + offline tiles | 14 | 25% | MapKit/Google/Leaflet baza; tiles RO | Modul harta; cache
8b. Integrare cu Sistemul GIS central (WMS/WFS) | 15 | 30% | Consum WMS+WFS server GIS central; Stereo70 vs WGS84; auth GIS; layere veterinary (focare, restrictii) | WMS/WFS client nativ; proj conv; layer mgr
9. Camera + foto + EXIF | 14 | 15% | Captura, watermark timestamp+geo, upload chunked | Modul foto; <200KB upload
10. Push notifications (APNs+FCM+web) | 12 | 15% | Server scheduling, deep linking | OneSignal/Firebase; topics
11. Autentificare ROeID (UI flow mobile) | 22 | 35% | ROeID docs limitate mobile; biometric + Keychain/Keystore | ROeID flow nativ; fallback parola
11b. Integrare IAM Keycloak (OAuth2 PKCE + token mgmt) | 10 | 20% | OAuth2 PKCE nativ via Keycloak; refresh token rotation; biometric unlock pt. token; JWT validation locala (JWKS cache); silent renewal | AppAuth SDK iOS+Android; PKCE; token storage criptat
12. API backend sincron (BND-SNIIA + Portal + LIMS REST) | 32 | 25% | API client SDK; retry; paginare | SDK; error mapping; offline queue
12b. Consum ESB / mesaje async | 18 | 25% | Abonare topic-uri ESB (rezultat analiza, status raportare, alerte); REST polling / WebSocket bridge; fallback push | ESB consumer adapter; WebSocket bridge
12c. Telemetrie utilizare -> ETL/DW | 5 | 10% | Evenimente utilizare (raportare creata, login) publicate spre ETL pt. DW; producer events; nu necesita ETL direct | Event publisher SDK; schema; batch upload
13. Offline-first + sync queue | 22 | 25% | Conectivitate intermitenta rural; raportari offline sync | Queue locala; background sync
14. Localizare RO + i18n | 8 | 5% | RO+EN; format date/numere | i18n strings
15. A11y WCAG 2.1 AA | 22 | 20% | VoiceOver+TalkBack+NVDA; contrast 4.5:1 | A11y compliant; audit
16. Securitate OWASP MASVS L1 | 22 | 25% | Cert pinning, jailbreak, secure storage, ofuscare | Security controls; audit intern
17. Testare unit + integration | 30 | 10% | JUnit/XCTest; cov > 70% | Coverage; CI gate
18. Testare E2E | 25 | 15% | Maestro/Appium/Detox; critical journeys | E2E suite; CI
19. Manual QA pe device fizic (8-10) | 28 | 15% | 4 iOS + 6 Android + tablet | Device matrix; defect log
20. Pentest mobil extern + remediere | 15 | 25% | MASVS L1 audit; 2 cicluri | Pentest; remediere; re-test
21. Publicare stores (Apple+Google+Magazin RO) | 18 | 40% | Apple review strict apps gov; 3-5 cicluri | Listing; screenshots; privacy
22. Doc tehnica + user guide RO+EN | 15 | 5% | Manual + admin guide push + release notes | PDF; in-app help; video
23. Materiale instruire | 10 | 5% | Curs DSVSA + medici vet care vor instrui cetatenii | Slide deck; ghid trainer
24. UAT | 28 | 20% | Multi-stakeholder 2-3 sapt | UAT plan; defect log; sign-off
25. Go-live + hyper-care 2 sapt | 18 | 15% | Deploy; push; monitoring; on-call | Production release
SUBTOTAL implementare initiala |  |  | Risc mediu ponderat
Buffer contingency (20%) |  |  |  | Standard proiecte gov IT
TOTAL IMPLEMENTARE + BUFFER
MENTENANTA + SUPORT (3 ani conform CdS)
Faza | Estimat man-day | Risk % | Descriere risc | Note / Livrabile
Mentenanta + suport L2+L3 (per AN; 3 ani CdS) | 250 | 25% | iOS+Android lanseaza versiuni majore anual; deprecari SDK; politici stores; CVE-uri MASVS; bug fixes; SLA L2 4h + L3 escaladare arhitect | BREAKDOWN/AN: ~80z corrective + ~70z adaptive (OS noi, SDK refresh) + ~50z perfective + ~50z on-call. ~1.2 FTE.
TOTAL MENTENANTA 3 ani (cumulativ) |  |  |  | Conform CdS - garantie L2+L3 pe 3 ani

## HL7
Estimare efort - HL7 gateway LIMS (3.4.3.3.3.2, pg.94-96 CdS)
Scope: Gateway HA HL7; ADT/ORM/ORU/MDM/ACK; mTLS+MLLP; queue+retry+DLQ; integrare 3 institute LIMS reale; IAM Keycloak (JWT); audit -> ETL/DW; 1000+ msg/sec; 3 ani garantie.
Faza | Estimat man-day | Risk % | Descriere risc | Note / Livrabile
1. Analiza cerinte + HL7 version assessment | 15 | 25% | Investigare LIMS la IDSA, IISPV, ICBMV; v2.5.1/v2.8/FHIR R4? | Assessment; recomandare versiune
2. Mapping mesaje HL7 veterinary | 22 | 30% | HL7 std uman; veterinary mai putin | Mapping ADT/ORM/ORU/MDM; custom
3. Arhitectura gateway HA | 12 | 10% | Cluster activ-pasiv; idempotency; DLQ | ADR; sequence; HA topology
4. Selectie produs + setup | 10 | 15% | Mirth vs Iguana (~30k) vs InterSystems (~50k) | Vendor eval; PoC
5. Setup gateway + canale baseline | 14 | 15% | Mirth cluster; per institut | Mirth prod+dev; canale
6. Transformatori SQL -> HL7 outbound | 30 | 25% | JS transformers; 4-5 mesaje; diacritice RO | Channels; tests
7. Transformatori HL7 -> SQL inbound | 25 | 25% | Parse; validare; error handling | Parsere; validators; storage
8. Queue + retry + DLQ + idempotency | 18 | 20% | Status mesaje; idempotency keys; exp backoff | Tabela; cron retry; DLQ
9. Audit logging (GDPR sanitar) | 14 | 15% | Audit acces; retention 7 ani; anonimizare | Schema; retention; SIEM
10. Backup + restore | 8 | 10% | Cerinta CdS; daily backup; restore drill | Script; runbook
11. API REST in fata (app mobila + portal) | 22 | 20% | REST; JWT; OpenAPI; rate limit | OpenAPI; controller; JWT
11b. Integrare IAM Keycloak + audit ETL/DW | 10 | 15% | Validare JWT cu JWKS Keycloak; claims-based authorization per endpoint; audit mesaje HL7 publicat catre ETL/DW pt. raportare cantitativa + conformitate GDPR | Keycloak adapter; JWKS cache; audit publisher
12. Integrare cu Sistem responsive (3.4.3.3.3.1) | 14 | 15% | Joint design; shared schema | API contract; integration tests
13. TLS mutual + MLLP over TLS | 18 | 25% | MLLP putine produse RO nativ; mTLS; cert rotation | mTLS config; MLLP framing
14. Monitorizare Grafana + Prometheus | 10 | 10% | Queue depth, msg/sec, error rate, latency | Dashboard; alerte
15. Testare unit + integration cu HAPI | 28 | 15% | Sintetic msg; mock LIMS; edge cases | JUnit; HAPI simulator
16. Testare conformitate HL7 | 18 | 20% | HAPI Conformance / Caristix | Conformance profile; raport
17. Testare interop cu LIMS REAL (3 institute) | 45 | 45% | CEL MAI MARE RISC: 3 institute, dialecte HL7, custom segments; 3 cicluri joint test | Joint testing; defect fix; sign-off
18. Performance testing | 12 | 15% | Target 1000+ msg/sec; load test | Load report; perf baseline
19. Doc tehnica administratori | 12 | 5% | Admin guide; troubleshooting | Admin guide; runbook
20. Doc conformitate + mesaje suportate | 8 | 5% | Spec compliance pt. evaluare | Spec doc; tabel mesaje
21. UAT beneficiar | 22 | 25% | Mesajele HL7 nu se valideaza vizual usor | UAT plan; defect log
22. Pre-prod + go-live (paralel-run 4 sapt) | 18 | 25% | Paralel-run; reconciliere zilnica | Deploy; paralel-run; cutover
23. Hyper-care 4 sapt | 14 | 15% | On-call 24/7 prima sapt | On-call; war room
SUBTOTAL implementare initiala |  |  | Risc mediu ponderat
Buffer contingency (20%) |  |  |  | Standard proiecte gov IT
TOTAL IMPLEMENTARE + BUFFER
MENTENANTA + SUPORT (3 ani conform CdS)
Faza | Estimat man-day | Risk % | Descriere risc | Note / Livrabile
Mentenanta + suport L2+L3 (per AN; 3 ani CdS) | 200 | 20% | HL7 stabil dar update-uri LIMS adaptari; SLA obligatoriu; CVE-uri Mirth/Java patch prompt; cert mTLS rotation 1-2 ani | BREAKDOWN/AN: ~60z corrective + ~50z adaptive (LIMS terte, cert, CVE) + ~40z perfective + ~50z on-call. ~1.0 FTE.
TOTAL MENTENANTA 3 ani (cumulativ) |  |  |  | Conform CdS - garantie L2+L3 pe 3 ani

## Portal
Estimare efort - Portal Servicii Publice (3.4.3.3.2, pg.83-86 CdS)
Scope: Portal multi-stakeholder (cetateni+firme+medici vet) cu 56 servicii; 185k useri/an; 46 institutii; ROeID + IAM Keycloak broker federat; 8 integrari externe; ESB intern + GIS central; ETL events + BI embed; BPM; PWA; A11y; OWASP; 3 ani garantie.
Faza | Estimat man-day | Risk % | Descriere risc | Note / Livrabile
1. Analiza cerinte + 46 institutii stakeholderi | 60 | 20% | 46 institutii; 3 tip useri; 56 servicii; 15-20 workshops | User stories; catalog; backlog
2. UX research + persona + journey | 45 | 15% | Persona cetatean/firma/medic vet; 56 servicii × 3-4 states | Personas; journey; blueprints
3. IA + sitemap taxonomie | 32 | 15% | Taxonomie pe tip user; search faceted | Sitemap; navigation tree
4. UI design system + brand + componente | 52 | 15% | Atomic 100+ comp; tokens; responsive | Figma DS; tokens
5. Wireframes Lo-Fi 56 servicii (~200 ecrane) | 80 | 20% | 56 × 3-4 ecrane medie | Wireframes; flow
6. Hi-Fi mockups responsive | 75 | 15% | 200 ecrane × 3 variante = 600 frame-uri | Hi-Fi; prototype
7. A11y WCAG 2.1 AA design review | 25 | 15% | AA mandator gov; remediere | Audit; design corectat
8. Arhitectura + ADR + setup | 35 | 10% | Microservices vs mono; K8s vs VM | ADR; HLD; CI/CD
9. FE - shell + navigation + state | 40 | 15% | SPA; lazy loading; Redux/Pinia; SSR opt | Shell; routing; auth gate
10. FE - design system implementation | 50 | 15% | Storybook; 100+ comp; a11y per comp | Storybook; coverage > 70%
11. FE - homepage + catalog + search | 45 | 15% | 56 servicii; Elasticsearch; filters | Catalog; search UI
12. FE - 56 servicii formulare (~4z/serviciu) | 224 | 25% | 56 × 4z medie; validare; auto-save | 56 formulare
13. FE - dashboard + istoric + notificari | 45 | 15% | Personal area; notification center | Dashboard; profil
14. FE - CMS editorial content | 35 | 10% | News, FAQ, ghiduri PDF, regulamente | CMS frontend
15. FE - PWA features | 25 | 15% | SW; offline cache; push web; install | PWA installabila
16. BE - API gateway + microservices | 40 | 15% | Kong/Krakend; decompozitie; rate limit | Gateway config
17. BE - auth ROeID + RBAC business per 56 servicii | 35 | 30% | ROeID OAuth2 UI flow; MFA; RBAC business per serviciu | Auth service; ROeID adapter; RBAC matrix
17b. Integrare IAM Keycloak (broker federat + SSO + user federation) | 25 | 25% | Keycloak ca broker federat: ROeID -> Keycloak -> toate componentele SIDISVA; SSO server-side intre Portal+DMS+LIMS+BND; user federation LDAP; claims mapping; theme custom ANSVSA; admin console Keycloak | Keycloak realm; IdPs ROeID+LDAP+local; claims mappers; client config per componenta
18. BE - 56 servicii business logic (~6z/serviciu) | 336 | 25% | 56 × 6z BE medie; validari, persistence, gen docs | 56 servicii; OpenAPI; DTO
19. BE - workflow engine BPM | 60 | 20% | Autorizare 30-60z multi-nivel; BPMN; DMS integration | BPM; workflows; escalare
20. BE - storage + AV + e-signature | 28 | 15% | MinIO/S3; ClamAV; qualified signature | Storage; AV; e-sign
21. BE - notificari multi-channel | 35 | 15% | Email + SMS + push; templating; opt-in | Notification service; templates
22. BE - integrari externe (8 sisteme: ROeID, PNI, PCUe, ONRC, APIA, ANCPI, ANARZ, CMV) | 140 | 35% | 8 × ~17.5z medie; RISC: API parteneri | 8 adaptari; circuit breakers
22b. Integrare ESB intern (mesaje async cross-component) | 50 | 25% | Portal subscribe ESB de la DMS (status cerere), BND-SNIIA (registre), LIMS (rezultate), Supraveghere (alerte); publicare events Portal -> alte comp; schema versioning; DLQ; idempotency; contract testing | ESB consumers/producers; topic-uri; schema registry; saga
22c. Integrare Sistem GIS central (servicii cartografice) | 42 | 25% | Consum WMS/WFS pt. hărti tematice publice (focare boli, distributie medici vet, restrictii); editor coordonate exploatatii in autorizari; Stereo70; cache server; auth GIS | GIS client serverside; WMS/WFS proxy; cache; editor coords
23. BE - audit + GDPR compliance | 28 | 15% | Audit Art. 30; retention; endpoints Art. 15-22 | Audit service; retention; GDPR endpoints
24. BE - contorizare servicii (3.4.2.13) - logica Portal | 22 | 10% | Contorizare folosire servicii (logica de business + persistence) | Contorizare service; tabele evenimente
24b. Integrare ETL / DW (event publisher contorizare + audit) | 18 | 15% | Portal publica events catre ETL: utilizare servicii, audit, statistici GDPR; alimentare DW pt. EFSA + ANSVSA mgmt; back-pressure | Event publisher; schema DW; reliable delivery
24c. Integrare BI dashboards (embed in admin console) | 10 | 10% | Embed dashboards BI (Oracle Analytics/Power BI) in admin console pt. useri ANSVSA cu drept; SSO via Keycloak; iframe sandboxed | BI embed adapter; SSO bridge
25. BE - admin console | 45 | 10% | Self-service admin servicii/content/useri/roluri | Admin console; permisiuni
26. Securitate WAF + pentest extern | 50 | 25% | OWASP Top 10; pentest 2 cicluri | Pentest; remediere; WAF rules
27. Performance & scalability (185k useri) | 35 | 20% | Load test 1000 conc; Redis; CDN | Perf baseline; load report
28. Testare unit FE+BE | 70 | 10% | Coverage > 70% | Coverage report
29. Testare integration | 95 | 15% | 56 servicii × BE + 8 integrari; mocks | Test suite; mocks
30. Testare E2E | 50 | 15% | Cypress/Playwright; cross-browser | E2E suite
31. Testare A11y | 22 | 15% | Axe + manual screen readers | A11y report
32. Testare conformitate Anexa F | 25 | 10% | 1294 cerinte; trace matrix | Test pe matrice; raport
33. Doc tehnica + OpenAPI | 38 | 5% | OpenAPI 8 integrari + API public app mobila | OpenAPI 3.0; dev portal
34. Doc utilizator + video | 35 | 5% | Manual RO+EN; video tutorials top 20 | Manual PDF; 20 videos
35. UAT multi-stakeholder | 70 | 20% | UAT 4-6 sapt; 3 cicluri | UAT plan; defect log
36. Migrare continut existent | 28 | 30% | Volum NECUNOSCUT | Migration plan; scripts
37. Pre-prod + go-live faze | 45 | 15% | 3 faze: 10-15 -> 20-25 -> 56 | Deploy plan; phased release
38. Operationalizare + handover | 25 | 10% | KT ANSVSA; runbook-uri; SLA | Runbooks; SLA matrix
SUBTOTAL implementare initiala |  |  | Risc mediu ponderat
Buffer contingency (20%) |  |  |  | Standard proiecte gov IT
TOTAL IMPLEMENTARE + BUFFER
MENTENANTA + SUPORT (3 ani conform CdS)
Faza | Estimat man-day | Risk % | Descriere risc | Note / Livrabile
Mentenanta + suport L2+L3 (per AN; 3 ani CdS) | 900 | 25% | Portal mare 56 servicii + 8 integrari externe + 185k useri = mentenanta substantiala; CVE-uri OWASP frecvent; APIs externe schimba periodic; modificari legislative impact servicii; SLA L2 4h + L3 escaladare; on-call 24/7 servicii tier-1 | BREAKDOWN/AN: ~300z corrective (56 servicii P1/P2 + fix integrari) + ~200z adaptive (compat APIs, dependinte, legislativ) + ~200z perfective + ~200z on-call SLA 24/7 servicii cu termen legal. ~4.3 FTE.
TOTAL MENTENANTA 3 ani (cumulativ) |  |  |  | Conform CdS - garantie L2+L3 pe 3 ani